Strategic Plan

2018-2020

Mission Statement: Adoptions of Indiana seeks to identify and meet the needs of adoptees and birth & adoptive families through compassionate and comprehensive adoption services.

Vision Statement: Every child in a loving and caring home. Every parent and adoptee supported. Every community enlightened.

Critical Success Factors & Tactics:

- Provide high quality, effective, easily accessible programs and services

| Tactic | Who is responsible | Complete by: |  |  |
| --- | --- | --- | --- | --- |
|  |  | 2018 | 2019 | 2020 |
| Increase the number of expectant mothers who contact AOI for options counseling and adoption services - Assign office manager to be responsible for handling online chat with expectant women during normal business hours | Addison Kane | For the calendar year, keep accurate stats for contacts so we have a baseline | Increase contacts 10% over 2018 | Increase contacts 10% over 2019 |
| Improve and maintain client satisfaction with services - Develop and implement post-service survey to measure satisfaction. Seeking 95% approval - Results to be reviewed quarterly by staff and board | Addison Kane | Develop survey by EOY 2017 (done) Survey AOI placement families January 2018 Review results quarterly | Expand survey to outside clients January 2019, continue quarterly review |  |
| Improve education of Kirsh out-of-state families who are going to have placement in Indiana - Develop and disseminate webinar regarding expectations, respectfulness for birth mothers and staff during hospital time | Amy Nicholas | Develop by October 2018 | Disseminate 1st quarter 2019 | Expand webinar offerings to cover prenatal opiate exposure, other issues |
| Increase networking and support among birth parents in Indiana - By understanding their needs and creating low-pressure, social events to build community | Meg Sterchi | Provide 4 events: 5K, Mother’s Day, Christmas, Chef JJ “team building” event | Same events as 2018, plus develop network based on Chef JJ events to create supportive “matches” between experienced and new birth mothers. |  |
| Create and enforce minimum standards for working with any attorney on a referral case (include consequences for failure to meet the standards) | Meg (with Jen & Amy) | Create by 12/2017 | Implement January 2018 |  |

- Improve AOI’s financial strength and viability

| Tactic | Who is responsible | Complete by: |  |  |
| --- | --- | --- | --- | --- |
|  |  | 2017 | 2018 | 2019 |
| Do research to determine whether to move ahead with becoming able to bill for services under Medicaid Research reimbursable codes to see if there are easy “tweaks” to match what we do to billable services Find a psychologist willing to work with us to make counseling services billable | Julie Meg | Research by 12/17 | Discuss with psychologist 1Q January |  |
| Present “Medicaid 101” to staff | Julie | On 9/11 during staff meeting | - | - |
| Draft “how to” flyer about Medicaid for expectant parents | Julie and Addison | By 11/15/2017 |  |  |
| Turn Anthem into a significant donor | Julie/Meg | $3,500 October | $5,000 (October) | $5,000 (October) |
| Tap adoptive grandparents to become a “guild” to help with social outreach and fundraising |  |  |  | Implement by 2Q |
| Create Fundraising plan - Thanksgiving request letter - Major Gift plan ($2K-$10K) - Develop 2018 plan, including engaging existing families and communicating the gap between what they paid for services, and what we provide. - 2018 Major Gift plan for 2-3 gifts ($2K-$10K) - Develop outreach presentation for clubs/organizations who may share goals with us | Addison (w/board input) | draft by 10/31 (2018 goal: 1-2 gifts, plan by EOY 2017) | draft by 10/31 2019 goal: 2-3 gifts play by EOY 10`8 1Q EOY 2Q | draft by 10/31 2020 goal: 3-4 gifts, plan by EOY 2017 |

- Recruit, retain, and develop a highly effective staff and board of directors

| Tactic | Who is responsible | Complete by: |  |  |
| --- | --- | --- | --- | --- |
|  |  | 2017 | 2018 | 2019 |
| Continue to build a competent board by a) identifying gaps in expertise and b) each board member recruiting at least 1-2 potential candidates with that expertise to be considered | All board members | Build board to 6 by EOY, including financial expertise | Expand board to 8 by EOY – focus on diversity factors (male, LBGT, non-Caucasian), and social connections to help us connect with “movers and shakers” |  |
| Interview each staff member to understand their specific roles, responsibilities, and needs in order to gain a wider knowledge of the agency’s programs and services (in order to effectively monitor, support, and strengthen them) Develop projects and/or policy changes based on those meetings | All board members to participate in at least one interview (all staff members to be interviewed) |  | Meet in January Implement changes as appropriate throughout 2018 | Meet in January Implement changes as appropriate throughout 2019 |
| Create and implement an annual evaluation process for board members and Executive Director | Jenny/Emily |  | Create by EOY | Implement 1Q |
| Recruit and hire a part -time staff person to assume more of Amy’s birth parent responsibilities to free her up to do more clinic and hospital education | Meg | Recruiting is underway | Hire by July |  |

- Effective public voice that targets and differentiates multiple audiences

| Tactic | Who is responsible | Complete by: |  |  |
| --- | --- | --- | --- | --- |
|  |  | 2017 | 2018 | 2019 |
| Increase the level of adoption awareness among hospital and clinic staff throughout Indiana - Present to staff and be available for options counseling at all 19 Planned Parenthood locations in Indiana - Present at hospitals/clinics each month | Amy | 3Q & 4Q (done) | Throughout the year 2 per month | Throughout the year 3 per month |
| Improve the quality of adoptive services provided by others by engaging Family to Family to help establish best practices within hospitals in Indiana - Cite Family to Family in our hospital education materials - Put Indiana on F-t-F’s “radar” for next state to move into - Leverage our relationship with St. Vincent to encourage them to invite F-t-F | Meg |  | Implement by 2Q Implement by 3Q, continue into 2019 Implement by 4Q, continue into 2019 |  |