| Rev. 9/22/18 22ZERO – Priority List – Year One |  |  |
| --- | --- | --- |
| Task | Due Date | Completion Date |
| Educate WH American Legion on PTS | 6/1/18 | 5/1/18 |
| Build a Vision Board | 6/13/18 | 6/20/18 |
| Rooftop University on Active Listening | 6/13/18 | 6/19/18 |
| Follow-up on Marketing Quote | 6/13/18 | 6/22/18 |
| Submit IRS Form 1023 | 6/25/18 |  |
| Strategic Planning Sessions / Formalize mission, vision, values | 7/1/18 | 7/4/18 |
| Write Fundraising Plan | 7/1/18 |  |
| Build a “Story Catcher” Journal | 7/1/18 | 7/1/18 |
| Create list of potential donors | 7/1/18 | 7/21/18 |
| Appoint Board of Directors (three members) | 7/1/18 | 6/20/18 |
| Research existing therapies (accessibility, success, $, proliferation…) | 7/1/18 |  |
| Begin contacting potential donors | 7/7/18 |  |
| Identify means to communicate with VSOs & “get the word out” | 7/7/18 | 8/1/18 |
| Finalize logo & graphic design | 8/1/18 | 8/1/18 |
| Share story with three other organizations | 8/1/18 | 8/13/18 |
| Read American Psychosis by E. Fuller Torrey | 8/1/18 | 6/20/18 |
| Identify qualified providers | 8/1/18 |  |
| Complete Marketing & Media Plan | 8/1/18 |  |
| Identify silos | 8/15/18 |  |
| List Key Leaders in positions of influence | 8/15/18 |  |
| Develop a Quick Reference Guide with key statistics | 8/15/18 |  |
| Identify relevant leaders to share story | 8/15/18 |  |
| Research history of mental health system | 8/31/18 | 8/31/18 (ongoing) |
| Website designed & operational | 9/1/18 |  |
| Facebook operational | 9/1/18 | 6/12/18 |
| Identify group of veterans most at risk. | 9/1/18 | 7/4/18 |
| Meet with five relevant leaders, share story, & “plant seeds” | 9/1/18 | 9/1/18 |
| “How Can I Help” Packet for Volunteers | 9/1/18 |  |
| Meet with service organizations to discuss PTS (let’s lose the D) – separate campaign | 3/1/19 |  |
| Determine process to vet service organizations. | 10/15/18 |  |
| Identify 10 Providers who desire to be qualified | 11/1/18 |  |
| Research and identify grant opportunities. | 5/1/19 |  |
| Determine eligibility & requirements to become qualified provider | 12/1/18 | 9/1/18 |
| Begin training at MB ACAP/Story (MacDill AFB) | 2/1/19 |  |
| Define/Plan/Write out details of Battle Buddy Program (Polk County) | 2/1/19 |  |
| Letters to American Legion Commanders | 2/1/19 |  |
| Revisit Professional Video Idea | 2/1/19 |  |
| Begin collaborating with organizations | 3/1/19 |  |
| Recruit & Train Five Battle Buddy Mentors | 5/1/19 |  |
| Raise $500K | 5/1/19 |  |
| Develop diverse list of vetted organizations for collaboration | 5/1/19 |  |
| Begin contacting leaders of collaboration organizations – ongoing | 5/1/19 |  |
| Identify resources to help build provider list | 5/1/19 |  |
| Record 3 Podcasts | 5/1/19 |  |
| Guest on Radio Talk Show | 5/1/19 |  |
| Author 2 Editorials (Op-Eds) | 5/1/19 |  |

Rev 9/22/18